## Report
[Project Title] | [13 empty] | [Company Name / Logo]
Earned Value Analysis Report
| Prepared By: | [Manager's Name]
| Date: | [Report Date]
[42]
| For Period: | Week 1
Summary:
El periodo indica semana terminada
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS)
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | ← You can change the labels for the periods (e.g. Week 1/2/3, Jan/Feb/Mar, etc.)
1.1 | Actividades de Inicio | 3.6 | 2 | 1 | 0.6 | [12 empty] | ← Enter or edit values in the light-blue cells.
1.1.1 | Desarrollo acta de constitución | 154 |  | 4 | 25 | 25 | 25 |  | 25 | 25 | 25
1.1.2 | Desarrollar el cronograma | 31 |  |  |  |  | 6 |  |  |  | 25
1.1.3 | Desarrollar el plan de gestión de proyecto | 10 | [5 empty] | 5 | 5
1.2 | Ejecución | 21 | [5 empty] | 7 | 7 |  | 7
1.2.1 | Contratar/asignar personal al proyecto | 35 | [7 empty] | 5 | 6 | 9 | 8 | 7 | 8 | 7
1.3 | Análisis y propuesta de solución | 17 |  |  | 5 | [7 empty] | 4 | 8 | 4 | 8
1.3.1 | Desarrollo de la arquitectura del sistema | 45 |  |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
1.3.2 | Diseño detallado de los componentes | 0
1.3.2.1 | Documentación de procesos (compra de boletos)
1.3.2.2 | Diagrama de clases (GAME y ADM)
1.3.2.3 | Casos de uso (GAME y ADM)
1.3.2.4 | Diagramas de actividades
1.3.3 | Dimensionamiento de infraestructura tecnológica
1.3.4 | Adquirir el equipamiento dimensionado
1.3.5 | Desarrollo de aplicaciones GAME y ADM
1.3.6 | Desarrollo de pruevbas de aplicaciones
1.3.7 | Integración de las aplicaciones ADM y GAME con la legacy
1.3.8 | Software LAPIS
1.3.6.1 | Compra de la aplicación
1.3.6.2 | Instalación y configuración
1.3.6.3 | Instalación remota del LAPIS en los terminales antiguos
Desarrolar el plan de transición
Adquirir los terminales indicados en el plan de transición
Entrenamiento a agentes con nuevos terminales
Negociación de contratos con ISP's
Instalación y configuración de centro de datos
Prueba de integración general
Cambio a protocolo TCP/IP
Marcha blanca (2 meses)
Mantenimiento a aplicaciones y hardware
Firma del acta de cierre del proyecto
Insert new rows above this one | [17 empty] | ← To add more tasks, insert rows above this one. You can or delete this row after you are done adding tasks.
| Total Budgeted Cost | 316.6 | 2 | 5 | 30.6 | 30 | 36 | 17 | 42 | 35 | 68 | 14 | 17 | 20 | 17 | 20
|  | Cumulative Planned Value (PV) | 2 | 7 | 37.6 | 67.6 | 103.6 | 120.6 | 162.6 | 197.6 | 265.6 | 279.6 | 296.6 | 316.6 | 333.6 | 353.6 | Línea azul en el gráfico
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 1 | 5 | 39.6 | 49.6 | 99.6 | 121.6 | 154.6 | 218.6 | 285.6 | 311.6 | 328.6 | 363.6 | 380.6 | 415.6 | Línea roja en el gráfico
|  | Cumulative Earned Value (EV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | Línea verde en el gráfico
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Schedule Variance (SV = EV - PV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Cost Performance Index (CPI = EV/AC) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Schedule Performance Index (SPI = EV/PV) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Estimated Cost at Completion (EAC) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Fecha oficial inicio de proyectos |  |  | 2015-04-10
Fecha presentación de proyectos terminados |  |  | 2015-07-17
Total semanas |  |  | 14
Note on A21: Work Breakdown Structure (WBS)
Note on C21: Total Budgeted Cost (TBC)
Note on D21: profesor: 10/04/15 al 17/04/15

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP).
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Actividades de Inicio | 3.6 | 15% | 50% | 60% | 70% | 80% | 90% | 95% | 96% | 97% | 98% | 99% | 100% | 99% | 100%
1.1.1 | Desarrollo acta de constitución | 154 |  | 25% | 30% | 60% | 75% | 90% | 100%
1.1.2 | Desarrollar el cronograma | 31 |  |  | 25% | 40% | 50% | 100% | 100%
1.1.3 | Desarrollar el plan de gestión de proyecto | 10 |  |  |  |  | 25% | 80% | 90% | 100%
1.2 | Ejecución | 21 | [5 empty] | 25% | 75% | 100%
1.2.1 | Contratar/asignar personal al proyecto | 35 | [6 empty] | 50% | 60% | 70% | 80% | 90% | 100% | 90% | 100%
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
#REF! | #REF! | #REF!
1.3 | Análisis y propuesta de solución | 17
1.3.1 | Desarrollo de la arquitectura del sistema | 45
1.3.2 | Diseño detallado de los componentes | 0
Insert new rows above this one
|  | Cumulative EV | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14
1.1 | Actividades de Inicio |  | Wk 1: 1; Wk 2: 1; Wk 3: 0.6
1.1.1 | Desarrollo acta de constitución |  | Wk 2: 3; Wk 3: 20; Wk 4: 5; Wk 5: 40; Wk 6: 5; Wk 7: 17; Wk 8: 25; Wk 9: 25
1.1.2 | Desarrollar el cronograma |  | Wk 5: 6; Wk 9: 25
1.1.3 | Desarrollar el plan de gestión de proyecto |  | Wk 6: 4; Wk 7: 3
1.2 | Ejecución |  | Wk 6: 7; Wk 7: 5; Wk 9: 7
1.2.1 | Contratar/asignar personal al proyecto |  | Wk 7: 3; Wk 8: 4; Wk 9: 6; Wk 10: 6; Wk 11: 8; Wk 12: 7; Wk 13: 8; Wk 14: 7
#REF! | #REF! |  | Wk 10: 15
#REF! | #REF! |  | Wk 3: 5; Wk 8: 30; Wk 12: 16; Wk 14: 16
#REF! | #REF! | bar: Wk 3
1.3 | Análisis y propuesta de solución |  | Wk 3: 8; Wk 11: 4; Wk 12: 7; Wk 13: 4; Wk 14: 7
1.3.1 | Desarrollo de la arquitectura del sistema |  |  |  |  | 5 | 4 | 6 | 5 | 5 | 4 | 5 | 5 | 5 | 5 | 5
1.3.2 | Diseño detallado de los componentes
Insert new rows above this one
|  | Total Actual Cost | 1 | 4 | 34.6 | 10 | 50 | 22 | 33 | 64 | 67 | 26 | 17 | 35 | 17 | 35
|  | Cumulative Actual Cost (AC) | 1 | 5 | 39.6 | 49.6 | 99.6 | 121.6 | 154.6 | 218.6 | 285.6 | 311.6 | 328.6 | 363.6 | 380.6 | 415.6